## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Setting up the project | 1 | 2024-07-18 | The very first thing I did was to read the assignment. I read through the requirements and user stories, then set up a scrum board, which could be found here( https://veerific.notion.site/1737773ccb264bc2bd56507020cc41fb?v=0b9c11f4d95345c58150d336a8281f05 ) I could work with during the assignment. Everything is set up, I can start with step 1, researching algorithms.
Researching Algorithms | 1 | 2024-07-18 | I read through this wikipedia article (https://en.wikipedia.org/wiki/Maze_generation_algorithm ) and chose three that I found either funny or interesting. I documented my research on it here ( https://veerific.notion.site/PCG-Algorithms-5fae05ac158943fcb3a81d7e1ad3db51 )
Implementing the first algorithm (US1) | 5 | 2024-07-19 | After choosing the algorithms, I started attempting to implement the first algorithm: DFS. I figured DFS would be relatively simple to start with and it's an algorithm I haven't used before, so I wanted to try it out with this assignment. Step one was to write a script that would handle the grid generation. I also wanted to see whether or not if it worked in the editor, so I immediately went to work with visualizing the generation by using simple 2D squares. After I completed the grid generation, I started working on the algorithm. (21/07/2024) After being stuck due to a small oversight in the grid generation and the amount of time I have left in this assignment, I decided to change my goals and instead focus on this single algorithm. I finally got the algorithm working, both technically and visually.
Improving the UI (US2, US3, US4) | 3 | 2024-07-21 | I started working on improving the UI. Based off the user stories, I already implemented some functionalities, like 'users can generate the grid via the editor/run time'. Buttons are already implemented in the interface that users can press. I started to implement the other requirements, such as adjusting the width/height along with restraints based on the US. (23/07/2024) I worked remotely somewhere else, but forget to push my previous commits to my git repo, meaning I had to redo the task on a different system. Once I've redone the lost work and the input restraints were implemented, I added a small regex function in order to make sure the user only inputs numbers. This way, I could avoid other errors such as an invalid input or an incorrect value. The final task I did was to make sure the UI scaled with the resolution, so it stays readable with a desktop, Ipad and IPhone resolution. I mostly solved this by making sure the UI objects stayed anchored in the corner and the canvas scaled with the screen size.
Making sure the maze is always visible, no matter the size of the screen (US2) | 3 | 2024-07-23 | US2 mentions that the maze must be visible at all times, so this is the next task I took up. At this point during development, the camera is static and when the maze generates with bigger sizes, it flows out of the screen. I had to decide between either resizing the maze to fit within the camera size, or to resize the camera to fit the whole maze. I first chose the latter, as I feel it would be easier to change one object, instead of potentially thousands. This step took a lot of trial and error, especially with trying to get the 250x250 fit in the screen with several aspect ratios. I eventually did an attempt with rescaling the maze itself, but that proved too complicated and switched back to resizing the camera. After a bit of help from a classmate, I did manage to be able to get the maze to be visible on screen, no matter it's size or the device.
Code Cleanup | 1 | 2024-07-23 | After finishing most of the tasks, I spent some time reformatting code. Made sure variables aren't public unless absolutely necessary, simplified some code and wrote comments where needed.
Attempt at improving performance with 250x250 maze (US2) | 1 | 2024-07-23 | At most sizes, the maze ran fine, but when going bigger with sizes like 250x250, unity struggles a lot. I tried some solutions to hopefully improve it's performance, such as marking objects as static so Unity can automatically perform static batching. After looking through forums for a bit, I stumbled upon one solution, namely combining the meshes. However, upon more research into mesh combining, I found out that Unity does that automatically with static objects. So I continued looking for other ways to hopefully improve performance. I decided to turn to Unity's profiler, hoping to figure out the biggest villain in this performance drop. After letting the profiler run it's course, I found that the renderers are the culprit. I already assumed as such but it was handy to fully confirm what was going on. I found this page (https://unity.com/how-to/project-configuration-and-assets) that lists a bunch of techniques and project settings that might help with performance, but none proved effective enough to deal with the FPS drop. I decided for now, I will let it be.
End Reflection |  | 2024-07-23 | In the end, I am a bit satisfied with the end product. I think next time, I would like to focus on how I could improve performance with bigger mazes. I saw another solution pass by, namely compute shaders. Seeing as I was reaching my own personal deadline, I couldn't pour in the time to properly research it and implement it in this project.
Total amount of hours | 15